## Agile Project Plan Sample
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Product Release | Alex B. | 2022-09-02 | 2022-10-10 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Alex B. |  | 2022-09-03 | 2022-09-13 | 10 | Complete
| Feature 1 |  | Frank C. |  | 2022-09-03 | 2022-09-07 | 4 | Complete
| Feature 2 |  | Jacob S. |  | 2022-09-07 | 2022-09-12 | 5 | Complete
| Feature 3 |  | Jacob S. |  | 2022-09-09 | 2022-09-13 | 4 | Overdue
| Sprint 2 |  | Jacob S. |  | 2022-09-16 | 2022-09-24 | 8 | In Progress
| Feature 4 |  | Alex B. |  | 2022-09-16 | 2022-09-17 | 1 | In Progress
| Feature 5 |  | Frank C. |  | 2022-09-17 | 2022-09-21 | 4 | Not Started
| Feature 6 |  | Shari W. |  | 2022-09-22 | 2022-09-24 | 2 | Not Started
| Sprint 3 |  | Shari W. |  | 2022-09-25 | 2022-10-05 | 10 | Not Started
| Feature 7 |  | Alex B. |  | 2022-09-25 | 2022-09-29 | 4 | Not Started
| Feature 8 |  | Kennedy K. |  | 2022-09-24 | 2022-10-02 | 8 | Not Started
| Feature 9 |  | Jacob S. |  | 2022-10-02 | 2022-10-05 | 3 | Not Started

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | IT Advising intranet software
| IT Advising #1 | Nichole Sherman | 2025-02-20 | 2025-05-02 |  |  |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  |  |  | 2025-02-20 | 2025-03-13
| Basic database structure | Backend | Austin Richardson, Evan Riley |  | 2025-02-20 | 2025-03-13 | 24 | Not started
| Finalize user interface | Frontend | Nichole Sherman |  | 2025-02-20 | 2025-03-13 | 24 | Not started
| Setup online database | Backend | All |  | 2025-02-20 | 2025-03-13 | 24 | Not started
Sprint 2
| Setup database query | Backend | Austin Richardson, Evan Riley |  | 2025-03-14 | 2025-04-03 | 24 | Not started
| Setup intranet view | Frontend | Nichole Sherman |  | 2025-03-14 | 2025-04-03 | 24 | Not started
| Finalize back-end | Backend | Austin Richardson, Evan Riley |  | 2025-03-14 | 2025-04-03 | 24 | Not started
Sprint 3
| Connect front-end to back-end | Both | All |  | 2025-04-04 | 2025-05-01 | 24 | Not started
| Setup account systems | Both | All |  | 2025-04-04 | 2025-05-01 | 24 | Not started
| Setup report system | Both | All |  | 2025-04-04 | 2025-05-01 | 24 | Not started